## Scenarios
NOAH Prototype — Scenario & Use Case Matrix
Prototype Build Plan — Option 3 (UC-07 → UC-10) + Narrative (UC-18, UC-20) + Canned/Pages + Packaging
PSC # | Scenario | PUC # | Prototype Use Case | Persona | Sprint | NOAH UC(s) | Acceptance Criteria | Priority | Claude Time
PSC-01 | Foundation — Dual-Mode Scaffold | PUC-01 | Vite + React + TS scaffold with dual-mode build | Dev | PS-01 | — | VITE_MODE=live¦canned drives both agent adapter and theme. Scaffold runs on fresh Windows laptop with pnpm. | P0 | 1-2h
PSC-01 | Foundation — Dual-Mode Scaffold | PUC-02 | Ollama client with JSON mode + health check | Dev | PS-01 | — | chatJSON() returns validated JSON or throws OllamaError; checkHealth() pings /api/tags. Unit tests green. | P0 | 2-3h
PSC-01 | Foundation — Dual-Mode Scaffold | PUC-03 | Document ingest (PDF + DOCX) with page spans + SHA-256 | Dev | PS-01 | — | Ingests .pdf (pdfjs-dist) and .docx (mammoth). Returns fullText + pages + hash. Errors on scanned/empty. | P0 | 2-3h
PSC-01 | Foundation — Dual-Mode Scaffold | PUC-04 | Port close-cycle simulation to React | Nike (viewer) | PS-01 | UC-13,14,15 | 4 phases (Pre-Close→Execute→Validate→Gate), 6 entities, event log, journey map. Matches NikeR2R-v4-Compare.html fidelity. | P0 | 3-4h
PSC-01 | Foundation — Dual-Mode Scaffold | PUC-05 | Port Copilot chat panel (scripted) | Nike (viewer) | PS-01 | UC-25 | Canned topic routing with 5+ keyword matches: close status, exceptions, contracts, accruals, default. | P1 | 1h
PSC-02 | Contract Attribute Extraction (UC-07) | PUC-06 | 27-attribute zod schema | Dev | PS-02 | UC-07 | Schema enumerates 27 attribute names; each field = {value, confidence, source_page}. Validation rejects malformed. | P0 | 0.5h
PSC-02 | Contract Attribute Extraction (UC-07) | PUC-07 | Extractor agent calling Qwen | Keven (demo) | PS-02 | UC-07 | Real Qwen JSON-mode call returns validated ContractAttributes. Retries once with correction prompt on bad JSON. | P0 | 2-3h
PSC-02 | Contract Attribute Extraction (UC-07) | PUC-08 | Agent adapter interface + LiveAgent | Dev | PS-02 | — | Agent interface has extract/risk/tech/accrual/narrative methods. LiveAgent emits step events for UI strip. | P0 | 1h
PSC-02 | Contract Attribute Extraction (UC-07) | PUC-09 | Contract queue screen | Keven (demo) | PS-02 | UC-08 | Drag-drop upload (.pdf/.docx). Seed contracts + uploaded list visible. Sorts by risk. | P0 | 2h
PSC-02 | Contract Attribute Extraction (UC-07) | PUC-10 | Contract review screen | Nike (viewer) | PS-02 | UC-07 | Document viewer + 27-attribute checklist + agent activity strip + confidence badges (green/amber/red). | P0 | 2-3h
PSC-02 | Contract Attribute Extraction (UC-07) | PUC-11 | Ollama pre-flight guard | Dev | PS-02 | — | Modal blocks /contracts and /narrative routes if Ollama is unhealthy; Retry re-checks. Close Cockpit still loads. | P1 | 0.5-1h
PSC-03 | Risk + Technical Accounting (UC-08, UC-09) | PUC-12 | Risk scoring (rules + LLM signal) | Dev | PS-03 | UC-08 | scoreRules + scoreLLM; category High/Med/Low; reasons[]. | P0 | 1-2h
PSC-03 | Risk + Technical Accounting (UC-08, UC-09) | PUC-13 | Technical accounting classifier | Dev | PS-03 | UC-09 | Detects ASC 840/842 leases + ASC 815 derivatives. Returns expense recognition method + requires_senior_review flag. | P0 | 2-3h
PSC-03 | Risk + Technical Accounting (UC-08, UC-09) | PUC-14 | Risk + flags UI | Nike (viewer) | PS-03 | UC-08,09 | Risk gauge + category badge + reasons panel. ASC tags with mandatory senior review banner when flagged. | P0 | 1-2h
PSC-04 | Accrual & JE (UC-10) | PUC-15 | Accrual inputs extractor (strings/dates only) | Dev | PS-04 | UC-10 | AccrualInputs type has NO numeric fields. LLM returns strings/dates; missing[] populated on low-confidence gaps. | P0 | 1-2h
PSC-04 | Accrual & JE (UC-10) | PUC-16 | Deterministic accrual math | Dev | PS-04 | UC-10 | Pure TS: straight-line pro-ration, GR/IR net (billedToDate subtracted), zero-period handling. TDD with 3+ cases. | P0 | 2-3h
PSC-04 | Accrual & JE (UC-10) | PUC-17 | JE builder | Dev | PS-04 | UC-10 | Two-line entry (DR Expense / CR Accrued Liability). Debits = credits. Reversal = 1st of next month. | P0 | 1h
PSC-04 | Accrual & JE (UC-10) | PUC-18 | Accrual agent orchestration | Dev | PS-04 | UC-10 | Extract → parse → math → build JE. Emits step events. Throws with field list on missing inputs. | P0 | 1h
PSC-04 | Accrual & JE (UC-10) | PUC-19 | Accrual proposal screen | Nike (viewer) | PS-04 | UC-10 | JE card (T-account), calc detail panel, clause traceability links, Approve button → close-store audit event. | P0 | 2-3h
PSC-05 | Narrative Agent — Variance & Exec Summary (UC-18, UC-20) | PUC-20 | Seed P&L dataset | Dev | PS-05 | UC-18,20 | 12-15 line items: current vs prior period, variance $ and %, drivers, entity split (NA/EMEA/GC/APLA). Rich enough for Qwen to ground. | P0 | 1-2h
PSC-05 | Narrative Agent — Variance & Exec Summary (UC-18, UC-20) | PUC-21 | Variance commentary agent | Dev | PS-05 | UC-18 | Qwen generates 2-3 sentence prose per line item grounded ONLY in supplied numbers. Key drivers + risk flags + confidence. | P0 | 1-2h
PSC-05 | Narrative Agent — Variance & Exec Summary (UC-18, UC-20) | PUC-22 | Executive summary agent | Dev | PS-05 | UC-20 | Takes close metrics + top variances + risks → headline + key highlights + risks + recommendation. Board-ready tone. | P0 | 1h
PSC-05 | Narrative Agent — Variance & Exec Summary (UC-18, UC-20) | PUC-23 | Adapter: narrative methods | Dev | PS-05 | — | Extend Agent interface with generateVarianceCommentary + generateExecutiveSummary. LiveAgent emits events. | P0 | 0.5h
PSC-05 | Narrative Agent — Variance & Exec Summary (UC-18, UC-20) | PUC-24 | Variance commentary screen | Nike (viewer) | PS-05 | UC-18 | Narrative route. P&L grid + per-row Generate button + side panel showing streaming prose, drivers, risks. Copy-to-clipboard. | P0 | 2h
PSC-05 | Narrative Agent — Variance & Exec Summary (UC-18, UC-20) | PUC-25 | Executive summary tab + Cockpit integration | Nike (viewer) | PS-05 | UC-20 | Narrative screen Exec Summary tab. Close Cockpit shows Generate Close Narrative button at Gate phase; navigates to /narrative?tab=exec&autorun. | P0 | 1-2h
PSC-06 | Canned Mode + GitHub Pages | PUC-26 | CannedAgent adapter (fixture replay) | Dev | PS-06 | — | Loads fixtures/<hash>.json for contracts, plus narrative fixtures keyed by line-item ID. Replays with 200-800ms step delays. | P0 | 1-2h
PSC-06 | Canned Mode + GitHub Pages | PUC-27 | Fixture generator script | Dev | PS-06 | — | pnpm generate-fixtures walks samples/acme/*.{pdf,docx} and seed-pnl, runs LiveAgent chain, writes fixtures/*.json. | P0 | 1h
PSC-06 | Canned Mode + GitHub Pages | PUC-28 | Sample contracts in place (5 supplied) | Keven (demo) | PS-06 | — | Contract_1_Advertising_Campaign, Contract_2_Professional_Services_Outsourcing, Contract_3_Insurance_MultiYear, Contract_4_Construction_Retail_Remodel, Contract_5_AWS_Enterprise — already in samples/acme/. | P0 | 0.5h
PSC-06 | Canned Mode + GitHub Pages | PUC-29 | GitHub Pages deploy workflow | Dev | PS-06 | — | On push to main: pnpm build:pages → deploy to gh-pages. Public URL loads Acme demo. | P0 | 1h
PSC-07 | Packaging & QA | PUC-30 | Full README + demo script | Keven (demo) | PS-Final | — | Both setup paths. 60-second demo script covering all 3 agent flows (contract, JE, narrative). Troubleshooting. | P0 | 2h
PSC-07 | Packaging & QA | PUC-31 | Prompt regression harness | Dev | PS-Final | — | pnpm test:prompts runs LiveAgent against 5 Acme contracts + narrative golden set; diffs against expected. | P1 | 1h
PSC-07 | Packaging & QA | PUC-32 | Playwright E2E (canned mode) | Dev | PS-Final | — | Upload → extract → review → propose → approve flow passes. Narrative tab generates commentary. Deterministic assertions. | P1 | 1-2h
PSC-07 | Packaging & QA | PUC-33 | Pre-commit hook blocking Deloitte docs | Dev | PS-Final | — | husky pre-commit rejects any staged file under samples/user/ (except .gitkeep). Blocks .pdf and .docx. | P0 | 0.5h
PSC-07 | Packaging & QA | PUC-34 | Dress rehearsal on clean machine | Keven (demo) | PS-Final | — | Fresh Windows laptop: clone → setup < 5 min → run full demo both modes including narrative. Polish rough edges. | P0 | 1-2h

## By Sprint
Prototype Sprints — Tasks, Files, Hours
Sprint | PUC # | Task | Persona | Files (create/modify) | Tests | Claude Time
PS-01 — Foundation | Scaffold + Ollama client + PDF/DOCX ingest + port scripted simulations
PS-01 | PUC-01 | Vite + React + TS scaffold with dual-mode build | Dev | package.json, vite.config.ts, src/main.tsx, src/App.tsx, tailwind.config.js | — | 1-2h
PS-01 | PUC-02 | Ollama client with JSON mode + health check | Dev | src/agents/ollama-client.ts | src/agents/ollama-client.test.ts | 2-3h
PS-01 | PUC-03 | Document ingest (PDF + DOCX) with page spans + SHA-256 | Dev | src/lib/ingest.ts (pdfjs-dist + mammoth) | src/lib/ingest.test.ts | 2-3h
PS-01 | PUC-04 | Port close-cycle simulation to React | Nike (viewer) | src/screens/CloseCockpit.tsx, src/store/closeStore.ts, src/components/{PhaseGrid,EntityList,EventLog}.tsx | manual smoke | 3-4h
PS-01 | PUC-05 | Port Copilot chat panel (scripted) | Nike (viewer) | src/screens/CopilotPanel.tsx, src/data/copilot-canned-answers.ts | manual smoke | 1h
PS-02 — UC-07 Contract Extraction | Real Qwen extraction of 27 attributes into contract review UI
PS-02 | PUC-06 | 27-attribute zod schema | Dev | src/agents/contract-schema.ts | src/agents/contract-schema.test.ts | 0.5h
PS-02 | PUC-07 | Extractor agent calling Qwen | Keven (demo) | src/agents/extractor.ts | src/agents/extractor.test.ts | 2-3h
PS-02 | PUC-08 | Agent adapter interface + LiveAgent | Dev | src/adapters/{agent-interface,live-agent,index}.ts | — | 1h
PS-02 | PUC-09 | Contract queue screen | Keven (demo) | src/screens/ContractQueue.tsx, src/store/contractStore.ts, src/data/seed-contracts.ts | manual smoke | 2h
PS-02 | PUC-10 | Contract review screen | Nike (viewer) | src/screens/ContractReview.tsx, src/components/{AgentActivityStrip,ConfidenceBadge,AttributeChecklist,DocViewer}.tsx | manual E2E | 2-3h
PS-02 | PUC-11 | Ollama pre-flight guard | Dev | src/components/OllamaGuard.tsx | manual failure test | 0.5-1h
PS-03 — UC-08 + UC-09 Risk/Tech-Acct | Risk scoring and ASC 840/842/815 classification
PS-03 | PUC-12 | Risk scoring (rules + LLM signal) | Dev | src/agents/risk.ts | src/agents/risk.test.ts | 1-2h
PS-03 | PUC-13 | Technical accounting classifier | Dev | src/agents/tech-accounting.ts | src/agents/tech-accounting.test.ts | 2-3h
PS-03 | PUC-14 | Risk + flags UI | Nike (viewer) | src/components/{RiskPanel,TechAccountingFlags}.tsx, modify ContractReview.tsx | manual smoke | 1-2h
PS-04 — UC-10 Accrual + JE | Extract → deterministic math → proposed JE with approval
PS-04 | PUC-15 | Accrual inputs extractor (strings/dates only) | Dev | src/agents/accrual-inputs.ts | src/agents/accrual-inputs.test.ts | 1-2h
PS-04 | PUC-16 | Deterministic accrual math | Dev | src/lib/accrual-math.ts | src/lib/accrual-math.test.ts (TDD) | 2-3h
PS-04 | PUC-17 | JE builder | Dev | src/lib/je-builder.ts | src/lib/je-builder.test.ts | 1h
PS-04 | PUC-18 | Accrual agent orchestration | Dev | src/agents/accrual.ts | — | 1h
PS-04 | PUC-19 | Accrual proposal screen | Nike (viewer) | src/screens/AccrualProposal.tsx, src/components/{JECard,CalcDetailPanel}.tsx | manual E2E | 2-3h
PS-05 — UC-18 + UC-20 Narrative Agent | Variance commentary + executive close narrative (3rd real-AI agent)
PS-05 | PUC-20 | Seed P&L dataset | Dev | src/data/seed-pnl.ts | — | 1-2h
PS-05 | PUC-21 | Variance commentary agent | Dev | src/agents/narrative.ts (generateVarianceCommentary) | src/agents/narrative.test.ts | 1-2h
PS-05 | PUC-22 | Executive summary agent | Dev | src/agents/narrative.ts (generateExecutiveSummary) | src/agents/narrative.test.ts | 1h
PS-05 | PUC-23 | Adapter: narrative methods | Dev | modify src/adapters/{agent-interface,live-agent}.ts | — | 0.5h
PS-05 | PUC-24 | Variance commentary screen | Nike (viewer) | src/screens/Narrative.tsx, src/components/{VarianceTable,CommentaryPanel}.tsx | manual E2E | 2h
PS-05 | PUC-25 | Executive summary tab + Cockpit integration | Nike (viewer) | src/components/ExecSummaryCard.tsx, modify CloseCockpit.tsx + Narrative.tsx | manual smoke | 1-2h
PS-06 — Canned Mode + Pages | Fixture-backed Acme theme for public GitHub Pages deployment
PS-06 | PUC-26 | CannedAgent adapter (fixture replay) | Dev | src/adapters/canned-agent.ts | src/adapters/canned-agent.test.ts | 1-2h
PS-06 | PUC-27 | Fixture generator script | Dev | src/scripts/generate-fixtures.ts | — | 1h
PS-06 | PUC-28 | Sample contracts in place (5 supplied) | Keven (demo) | samples/acme/Contract_{1..5}_*.docx (supplied), samples/README.md | manual review | 0.5h
PS-06 | PUC-29 | GitHub Pages deploy workflow | Dev | .github/workflows/pages.yml | CI run verification | 1h
PS-Final — Packaging & QA | Docs, regression tests, E2E, pre-commit guard, dress rehearsal
PS-Final | PUC-30 | Full README + demo script | Keven (demo) | README.md | — | 2h
PS-Final | PUC-31 | Prompt regression harness | Dev | src/scripts/prompt-regression.ts, tests/golden/*.expected.json | script passes | 1h
PS-Final | PUC-32 | Playwright E2E (canned mode) | Dev | playwright.config.ts, tests/e2e/contract-flow.spec.ts, tests/e2e/narrative.spec.ts | playwright green | 1-2h
PS-Final | PUC-33 | Pre-commit hook blocking Deloitte docs | Dev | .husky/pre-commit | manual: attempt to commit contract in samples/user → rejected | 0.5h
PS-Final | PUC-34 | Dress rehearsal on clean machine | Keven (demo) | — | dress rehearsal checklist | 1-2h
TOTAL |  | Estimated build time across all sprints |  |  |  | 44-62h

## By Persona
Prototype Build — Responsibilities by Persona
Dev
PUC # | Task | Sprint | Acceptance (summary) | Claude Time
PUC-01 | Vite + React + TS scaffold with dual-mode build | PS-01 | VITE_MODE=live¦canned drives both agent adapter and theme. Scaffold runs on fresh Windows laptop with pnpm. | 1-2h
PUC-02 | Ollama client with JSON mode + health check | PS-01 | chatJSON() returns validated JSON or throws OllamaError; checkHealth() pings /api/tags. Unit tests green. | 2-3h
PUC-03 | Document ingest (PDF + DOCX) with page spans + SHA-256 | PS-01 | Ingests .pdf (pdfjs-dist) and .docx (mammoth). Returns fullText + pages + hash. Errors on scanned/empty. | 2-3h
PUC-06 | 27-attribute zod schema | PS-02 | Schema enumerates 27 attribute names; each field = {value, confidence, source_page}. Validation rejects malformed. | 0.5h
PUC-08 | Agent adapter interface + LiveAgent | PS-02 | Agent interface has extract/risk/tech/accrual/narrative methods. LiveAgent emits step events for UI strip. | 1h
PUC-11 | Ollama pre-flight guard | PS-02 | Modal blocks /contracts and /narrative routes if Ollama is unhealthy; Retry re-checks. Close Cockpit still loads. | 0.5-1h
PUC-12 | Risk scoring (rules + LLM signal) | PS-03 | scoreRules + scoreLLM; category High/Med/Low; reasons[]. | 1-2h
PUC-13 | Technical accounting classifier | PS-03 | Detects ASC 840/842 leases + ASC 815 derivatives. Returns expense recognition method + requires_senior_review flag. | 2-3h
PUC-15 | Accrual inputs extractor (strings/dates only) | PS-04 | AccrualInputs type has NO numeric fields. LLM returns strings/dates; missing[] populated on low-confidence gaps. | 1-2h
PUC-16 | Deterministic accrual math | PS-04 | Pure TS: straight-line pro-ration, GR/IR net (billedToDate subtracted), zero-period handling. TDD with 3+ cases. | 2-3h
PUC-17 | JE builder | PS-04 | Two-line entry (DR Expense / CR Accrued Liability). Debits = credits. Reversal = 1st of next month. | 1h
PUC-18 | Accrual agent orchestration | PS-04 | Extract → parse → math → build JE. Emits step events. Throws with field list on missing inputs. | 1h
PUC-20 | Seed P&L dataset | PS-05 | 12-15 line items: current vs prior period, variance $ and %, drivers, entity split (NA/EMEA/GC/APLA). Rich enough for... | 1-2h
PUC-21 | Variance commentary agent | PS-05 | Qwen generates 2-3 sentence prose per line item grounded ONLY in supplied numbers. Key drivers + risk flags + confide... | 1-2h
PUC-22 | Executive summary agent | PS-05 | Takes close metrics + top variances + risks → headline + key highlights + risks + recommendation. Board-ready tone. | 1h
PUC-23 | Adapter: narrative methods | PS-05 | Extend Agent interface with generateVarianceCommentary + generateExecutiveSummary. LiveAgent emits events. | 0.5h
PUC-26 | CannedAgent adapter (fixture replay) | PS-06 | Loads fixtures/<hash>.json for contracts, plus narrative fixtures keyed by line-item ID. Replays with 200-800ms step ... | 1-2h
PUC-27 | Fixture generator script | PS-06 | pnpm generate-fixtures walks samples/acme/*.{pdf,docx} and seed-pnl, runs LiveAgent chain, writes fixtures/*.json. | 1h
PUC-29 | GitHub Pages deploy workflow | PS-06 | On push to main: pnpm build:pages → deploy to gh-pages. Public URL loads Acme demo. | 1h
PUC-31 | Prompt regression harness | PS-Final | pnpm test:prompts runs LiveAgent against 5 Acme contracts + narrative golden set; diffs against expected. | 1h
PUC-32 | Playwright E2E (canned mode) | PS-Final | Upload → extract → review → propose → approve flow passes. Narrative tab generates commentary. Deterministic assertio... | 1-2h
PUC-33 | Pre-commit hook blocking Deloitte docs | PS-Final | husky pre-commit rejects any staged file under samples/user/ (except .gitkeep). Blocks .pdf and .docx. | 0.5h
Keven (demo)
PUC # | Task | Sprint | Acceptance (summary) | Claude Time
PUC-07 | Extractor agent calling Qwen | PS-02 | Real Qwen JSON-mode call returns validated ContractAttributes. Retries once with correction prompt on bad JSON. | 2-3h
PUC-09 | Contract queue screen | PS-02 | Drag-drop upload (.pdf/.docx). Seed contracts + uploaded list visible. Sorts by risk. | 2h
PUC-28 | Sample contracts in place (5 supplied) | PS-06 | Contract_1_Advertising_Campaign, Contract_2_Professional_Services_Outsourcing, Contract_3_Insurance_MultiYear, Contra... | 0.5h
PUC-30 | Full README + demo script | PS-Final | Both setup paths. 60-second demo script covering all 3 agent flows (contract, JE, narrative). Troubleshooting. | 2h
PUC-34 | Dress rehearsal on clean machine | PS-Final | Fresh Windows laptop: clone → setup < 5 min → run full demo both modes including narrative. Polish rough edges. | 1-2h
Nike (viewer)
PUC # | Task | Sprint | Acceptance (summary) | Claude Time
PUC-04 | Port close-cycle simulation to React | PS-01 | 4 phases (Pre-Close→Execute→Validate→Gate), 6 entities, event log, journey map. Matches NikeR2R-v4-Compare.html fidel... | 3-4h
PUC-05 | Port Copilot chat panel (scripted) | PS-01 | Canned topic routing with 5+ keyword matches: close status, exceptions, contracts, accruals, default. | 1h
PUC-10 | Contract review screen | PS-02 | Document viewer + 27-attribute checklist + agent activity strip + confidence badges (green/amber/red). | 2-3h
PUC-14 | Risk + flags UI | PS-03 | Risk gauge + category badge + reasons panel. ASC tags with mandatory senior review banner when flagged. | 1-2h
PUC-19 | Accrual proposal screen | PS-04 | JE card (T-account), calc detail panel, clause traceability links, Approve button → close-store audit event. | 2-3h
PUC-24 | Variance commentary screen | PS-05 | Narrative route. P&L grid + per-row Generate button + side panel showing streaming prose, drivers, risks. Copy-to-cli... | 2h
PUC-25 | Executive summary tab + Cockpit integration | PS-05 | Narrative screen Exec Summary tab. Close Cockpit shows Generate Close Narrative button at Gate phase; navigates to /n... | 1-2h

## Traceability
Traceability: Prototype Scenario → PUC → NOAH UC → Sprint → Files → Hours
PSC | PUC # | Title | NOAH UC | Sprint | Files | Claude Time
PSC-01 | PUC-01 | Vite + React + TS scaffold with dual-mode build | — | PS-01 | package.json, vite.config.ts, src/main.tsx, src/App.tsx, tailwind.config.js | 1-2h
PSC-01 | PUC-02 | Ollama client with JSON mode + health check | — | PS-01 | src/agents/ollama-client.ts | 2-3h
PSC-01 | PUC-03 | Document ingest (PDF + DOCX) with page spans + SHA-256 | — | PS-01 | src/lib/ingest.ts (pdfjs-dist + mammoth) | 2-3h
PSC-01 | PUC-04 | Port close-cycle simulation to React | UC-13,14,15 | PS-01 | src/screens/CloseCockpit.tsx, src/store/closeStore.ts, src/components/{PhaseGrid,EntityList,EventLog}.tsx | 3-4h
PSC-01 | PUC-05 | Port Copilot chat panel (scripted) | UC-25 | PS-01 | src/screens/CopilotPanel.tsx, src/data/copilot-canned-answers.ts | 1h
PSC-02 | PUC-06 | 27-attribute zod schema | UC-07 | PS-02 | src/agents/contract-schema.ts | 0.5h
PSC-02 | PUC-07 | Extractor agent calling Qwen | UC-07 | PS-02 | src/agents/extractor.ts | 2-3h
PSC-02 | PUC-08 | Agent adapter interface + LiveAgent | — | PS-02 | src/adapters/{agent-interface,live-agent,index}.ts | 1h
PSC-02 | PUC-09 | Contract queue screen | UC-08 | PS-02 | src/screens/ContractQueue.tsx, src/store/contractStore.ts, src/data/seed-contracts.ts | 2h
PSC-02 | PUC-10 | Contract review screen | UC-07 | PS-02 | src/screens/ContractReview.tsx, src/components/{AgentActivityStrip,ConfidenceBadge,AttributeChecklist,DocViewer}.tsx | 2-3h
PSC-02 | PUC-11 | Ollama pre-flight guard | — | PS-02 | src/components/OllamaGuard.tsx | 0.5-1h
PSC-03 | PUC-12 | Risk scoring (rules + LLM signal) | UC-08 | PS-03 | src/agents/risk.ts | 1-2h
PSC-03 | PUC-13 | Technical accounting classifier | UC-09 | PS-03 | src/agents/tech-accounting.ts | 2-3h
PSC-03 | PUC-14 | Risk + flags UI | UC-08,09 | PS-03 | src/components/{RiskPanel,TechAccountingFlags}.tsx, modify ContractReview.tsx | 1-2h
PSC-04 | PUC-15 | Accrual inputs extractor (strings/dates only) | UC-10 | PS-04 | src/agents/accrual-inputs.ts | 1-2h
PSC-04 | PUC-16 | Deterministic accrual math | UC-10 | PS-04 | src/lib/accrual-math.ts | 2-3h
PSC-04 | PUC-17 | JE builder | UC-10 | PS-04 | src/lib/je-builder.ts | 1h
PSC-04 | PUC-18 | Accrual agent orchestration | UC-10 | PS-04 | src/agents/accrual.ts | 1h
PSC-04 | PUC-19 | Accrual proposal screen | UC-10 | PS-04 | src/screens/AccrualProposal.tsx, src/components/{JECard,CalcDetailPanel}.tsx | 2-3h
PSC-05 | PUC-20 | Seed P&L dataset | UC-18,20 | PS-05 | src/data/seed-pnl.ts | 1-2h
PSC-05 | PUC-21 | Variance commentary agent | UC-18 | PS-05 | src/agents/narrative.ts (generateVarianceCommentary) | 1-2h
PSC-05 | PUC-22 | Executive summary agent | UC-20 | PS-05 | src/agents/narrative.ts (generateExecutiveSummary) | 1h
PSC-05 | PUC-23 | Adapter: narrative methods | — | PS-05 | modify src/adapters/{agent-interface,live-agent}.ts | 0.5h
PSC-05 | PUC-24 | Variance commentary screen | UC-18 | PS-05 | src/screens/Narrative.tsx, src/components/{VarianceTable,CommentaryPanel}.tsx | 2h
PSC-05 | PUC-25 | Executive summary tab + Cockpit integration | UC-20 | PS-05 | src/components/ExecSummaryCard.tsx, modify CloseCockpit.tsx + Narrative.tsx | 1-2h
PSC-06 | PUC-26 | CannedAgent adapter (fixture replay) | — | PS-06 | src/adapters/canned-agent.ts | 1-2h
PSC-06 | PUC-27 | Fixture generator script | — | PS-06 | src/scripts/generate-fixtures.ts | 1h
PSC-06 | PUC-28 | Sample contracts in place (5 supplied) | — | PS-06 | samples/acme/Contract_{1..5}_*.docx (supplied), samples/README.md | 0.5h
PSC-06 | PUC-29 | GitHub Pages deploy workflow | — | PS-06 | .github/workflows/pages.yml | 1h
PSC-07 | PUC-30 | Full README + demo script | — | PS-Final | README.md | 2h
PSC-07 | PUC-31 | Prompt regression harness | — | PS-Final | src/scripts/prompt-regression.ts, tests/golden/*.expected.json | 1h
PSC-07 | PUC-32 | Playwright E2E (canned mode) | — | PS-Final | playwright.config.ts, tests/e2e/contract-flow.spec.ts, tests/e2e/narrative.spec.ts | 1-2h
PSC-07 | PUC-33 | Pre-commit hook blocking Deloitte docs | — | PS-Final | .husky/pre-commit | 0.5h
PSC-07 | PUC-34 | Dress rehearsal on clean machine | — | PS-Final | — | 1-2h

## Tech Inventory
Files & Modules Created per PUC
PUC # | Files Created/Modified | Tests | Sprint
PUC-01 | package.json, vite.config.ts, src/main.tsx, src/App.tsx, tailwind.config.js | — | PS-01
PUC-02 | src/agents/ollama-client.ts | src/agents/ollama-client.test.ts | PS-01
PUC-03 | src/lib/ingest.ts (pdfjs-dist + mammoth) | src/lib/ingest.test.ts | PS-01
PUC-04 | src/screens/CloseCockpit.tsx, src/store/closeStore.ts, src/components/{PhaseGrid,EntityList,EventLog}.tsx | manual smoke | PS-01
PUC-05 | src/screens/CopilotPanel.tsx, src/data/copilot-canned-answers.ts | manual smoke | PS-01
PUC-06 | src/agents/contract-schema.ts | src/agents/contract-schema.test.ts | PS-02
PUC-07 | src/agents/extractor.ts | src/agents/extractor.test.ts | PS-02
PUC-08 | src/adapters/{agent-interface,live-agent,index}.ts | — | PS-02
PUC-09 | src/screens/ContractQueue.tsx, src/store/contractStore.ts, src/data/seed-contracts.ts | manual smoke | PS-02
PUC-10 | src/screens/ContractReview.tsx, src/components/{AgentActivityStrip,ConfidenceBadge,AttributeChecklist,DocViewer}.tsx | manual E2E | PS-02
PUC-11 | src/components/OllamaGuard.tsx | manual failure test | PS-02
PUC-12 | src/agents/risk.ts | src/agents/risk.test.ts | PS-03
PUC-13 | src/agents/tech-accounting.ts | src/agents/tech-accounting.test.ts | PS-03
PUC-14 | src/components/{RiskPanel,TechAccountingFlags}.tsx, modify ContractReview.tsx | manual smoke | PS-03
PUC-15 | src/agents/accrual-inputs.ts | src/agents/accrual-inputs.test.ts | PS-04
PUC-16 | src/lib/accrual-math.ts | src/lib/accrual-math.test.ts (TDD) | PS-04
PUC-17 | src/lib/je-builder.ts | src/lib/je-builder.test.ts | PS-04
PUC-18 | src/agents/accrual.ts | — | PS-04
PUC-19 | src/screens/AccrualProposal.tsx, src/components/{JECard,CalcDetailPanel}.tsx | manual E2E | PS-04
PUC-20 | src/data/seed-pnl.ts | — | PS-05
PUC-21 | src/agents/narrative.ts (generateVarianceCommentary) | src/agents/narrative.test.ts | PS-05
PUC-22 | src/agents/narrative.ts (generateExecutiveSummary) | src/agents/narrative.test.ts | PS-05
PUC-23 | modify src/adapters/{agent-interface,live-agent}.ts | — | PS-05
PUC-24 | src/screens/Narrative.tsx, src/components/{VarianceTable,CommentaryPanel}.tsx | manual E2E | PS-05
PUC-25 | src/components/ExecSummaryCard.tsx, modify CloseCockpit.tsx + Narrative.tsx | manual smoke | PS-05
PUC-26 | src/adapters/canned-agent.ts | src/adapters/canned-agent.test.ts | PS-06
PUC-27 | src/scripts/generate-fixtures.ts | — | PS-06
PUC-28 | samples/acme/Contract_{1..5}_*.docx (supplied), samples/README.md | manual review | PS-06
PUC-29 | .github/workflows/pages.yml | CI run verification | PS-06
PUC-30 | README.md | — | PS-Final
PUC-31 | src/scripts/prompt-regression.ts, tests/golden/*.expected.json | script passes | PS-Final
PUC-32 | playwright.config.ts, tests/e2e/contract-flow.spec.ts, tests/e2e/narrative.spec.ts | playwright green | PS-Final
PUC-33 | .husky/pre-commit | manual: attempt to commit contract in samples/user → rejected | PS-Final
PUC-34 | — | dress rehearsal checklist | PS-Final