CONSTRUCTION SERVICES CONTRACT — RETAIL STORE RENOVATION

Contract Summary

| Contract No. | NK-SGA-CON-2026-0114 |
| --- | --- |
| Agreement Type | Fixed-Price Construction Contract with GMP Clause |
| Effective Date | March 1, 2026 |
| Substantial Completion | August 31, 2026 (6 months) |
| Final Completion | September 30, 2026 |
| Nike Entity | Nike Retail Stores, Inc. — Real Estate & Store Development |
| Property Address | Nike Georgetown, 1207 Wisconsin Ave NW, Washington, D.C. 20007 |
| Counterparty | Turner Construction Company |
| Counterparty Address | 375 Hudson Street, New York, NY 10014 |
| Counterparty Contact | Brian Gallagher, VP — bgallagher@tcco.com |
| Nike Contact | Amy Chen, Director Store Development — a.chen@nike.com |
| Contract Repository | Nike Contracts #CON-2026-0114 |

Section 1 — Scope of Work

Turner Construction Company ('Contractor') shall provide all labor, materials, equipment, and supervision necessary to renovate the Nike Georgetown retail store ('Project'), including:

- Complete interior demolition of existing 8,500 sq ft store (ground floor + mezzanine)

- Structural modifications: removal of two load-bearing walls per approved structural drawings

- MEP upgrades: HVAC replacement, electrical panel upgrade to 400A service, plumbing rerouting

- Custom millwork and fixture installation: Nike-standard modular display system (NDS-4.0)

- Flooring: polished concrete ground floor, engineered hardwood mezzanine

- Exterior façade: new storefront glazing system, LED lighting integration

- Digital infrastructure: conduit and backing for digital signage network

- Compliance upgrades: ADA accessibility improvements per current DC building code

All work shall conform to Nike's Global Store Design Standards Rev. 4.2 and approved construction drawings prepared by Gensler Architecture.

Section 2 — Financial Terms

| Contract Method | Fixed-Price with Guaranteed Maximum Price (GMP) |
| --- | --- |
| Base Contract Price | $4,200,000 |
| Owner's Contingency (5%) | $210,000 |
| Total GMP | $4,410,000 |
| Contractor's Contingency | $150,000 (included in Base; unused portion returned) |
| Retainage | 10% withheld through Substantial Completion; 5% thereafter |
| Billing Frequency | Monthly AIA G702/G703 Applications for Payment |
| Payment Terms | Net 30 from Nike's approval of Application for Payment |
| Liquidated Damages | $5,000/day for delay past September 30, 2026 final completion |
| Performance Bond | 100% of contract value — required prior to NTP |
| Payment Bond | 100% of contract value — required prior to NTP |

Schedule of Values (Abbreviated)

| Work Category | Value (USD) | % of Contract |
| --- | --- | --- |
| Demolition and Site Preparation | $280,000 | 6.7% |
| Structural Work | $420,000 | 10.0% |
| MEP (Mechanical, Electrical, Plumbing) | $890,000 | 21.2% |
| Storefront and Exterior | $650,000 | 15.5% |
| Interior Finishes and Flooring | $540,000 | 12.9% |
| Custom Millwork and Fixtures (NDS-4.0) | $780,000 | 18.6% |
| Digital Infrastructure | $190,000 | 4.5% |
| General Conditions and Overhead | $300,000 | 7.1% |
| Contractor Contingency | $150,000 | 3.6% |
| TOTAL BASE CONTRACT | $4,200,000 | 100.0% |

Section 3 — Accounting Treatment

3.1  Capitalization Analysis

This Project involves renovation of a Nike-leased retail premises. Accounting treatment requires assessment under ASC 840/842 (lease) and ASC 360 (PP&E).

| Lease Relationship | Nike leases the Georgetown premises under operating lease. Renovation costs are leasehold improvements. |
| --- | --- |
| Capitalization Treatment | Majority of costs capitalized as Leasehold Improvements (PP&E) per ASC 360-10 |
| Estimated Capitalized Amount | $3,780,000 (90% of contract value — structural, MEP, storefront, finishes, fixtures, digital infrastructure) |
| Expensed Amount | $420,000 (demolition costs, certain G&C costs, costs not meeting capitalization criteria per ASC 360) |
| Useful Life / Amortization | Lesser of remaining lease term (7 years remaining) or economic life — 7 years straight-line |
| Monthly Amortization | $45,000/month ($3,780,000 ÷ 84 months) |
| Asset Class | Leasehold Improvements — Retail |
| GL Account | 1530 — Leasehold Improvements / 6100 — Occupancy Expense (for expensed portion) |
| Cost Center | CC-4400 — Retail Store Georgetown |

3.2  Technical Accounting Checklist

| Embedded Derivative | None. Fixed USD pricing; no commodity or forex clauses. |
| --- | --- |
| Lease Component (ASC 842) | CRITICAL: Renovation does not modify the lease terms. No lease modification assessment required. Assets and ROU asset recognized separately. |
| Asset Retirement Obligation | Assess: Nike lease may contain restoration clause requiring removal of structural modifications at lease end. ARO to be recorded per ASC 410-20 if restoration reasonably estimable. |
| Milestone-Based Recognition | Costs capitalized as incurred per AIA payment applications; not milestone-expensed. |
| Go-Live / Placed in Service | Depreciation commences on date store reopens for retail operations (estimated October 2026). |
| Change Orders | Change orders >$25,000 require Nike VP Store Development approval. Capitalized or expensed per original cost categorization of affected scope. |
| Variable Consideration | Liquidated damages ($5K/day) recorded as reduction of capitalized cost if store opening is delayed. |
| SOX Relevance | Capital project >$1M requires Capital Appropriation Request (CAR) approval. Actual vs. budget tracked monthly. |

Section 4 — Schedule and Milestones

| Notice to Proceed (NTP) | March 1, 2026 — issued by Nike upon receipt of bonds |
| --- | --- |
| Demolition Complete | March 31, 2026 |
| MEP Rough-In Complete | May 15, 2026 |
| Interior Finishes Start | June 1, 2026 |
| Fixture Installation | July 15 – August 15, 2026 |
| Substantial Completion | August 31, 2026 |
| Punch List Period | September 1–30, 2026 |
| Final Completion | September 30, 2026 |
| Store Reopening | October 2026 (Nike operations — outside contract scope) |

Signature Block

| Nike Retail Stores, Inc. Authorized Signature Name: _________________________ Title: __________________________ Date: __________________________ |  | Turner Construction Company Authorized Signature Name: _________________________ Title: __________________________ Date: __________________________ |
| --- | --- | --- |

NOAH System Prototype — Document for AI Attribute Extraction Testing | NK-SGA-CON-2026-0114